## Product Backlog
MT08 - Markose Jacob, Pooja Kabra
Acme Ackermann Steering Controller
Product Backlog | [5 empty] | Use index colors to show revisions on task time
Unique ID | Task | Sprint | Estimated time (minutes) | Time after Iteration 1 | Time after Iteration 2 | Index | Information
Target Time
1 | Plan and Design |  | 0 | 0 | 0 |  | Revised Target Time
1.01 | Link github repo with travis CI | 1 |  |  |  |  | Actual Time Taken
1.02 | Link github repo with Coveralls | 1 |  |  |  |  | New Task Added
1.03 | Create skeleton code for Sensor class | 1
1.04 | Write constructors and destructors for Sensor class | 1
1.05 | Create unit tests for Sensor class
1.06 | Write getters for Sensor class | 1
1.07 | Write setters for Sensor class | 1
1.08 | Create skeleton code for RobotKinematics class | 1
1.09 | Write constructors and destructors for RobotKinematics class | 1
1.1 | Create unit tests for RobotKinematics Class
1.11 | Write getters for RobotKinematics class | 1
1.12 | Write setters for RobotKinematics class | 1
1.13 | Inspect source code | 1
1.14 | Create skeleton code for Controller class | 2
1.15 | Write constructors and destructors for Controller class | 2
1.16 | Create unit tests for Controller class
1.17 | Write getters for Controller class | 2
1.18 | Write setters for Controller class | 2
1.19 | Create skeleton code for ForwardKinematics class | 2
1.2 | Write constructors and destructors for ForwardKinematics class | 2
1.21 | Create skeleton code for InverseKinematics class | 2
1.22 | Inspect source code | 2
1.23 | Inspect unit test | 2
1.24 | Update readme | 2
2 | Implementation |  | 0 | 0 | 0
2.01 | Implement calculateHeadingError method | 3
2.02 | Create unit test for calculateHeadingError | 3
2.03 | Implement calculateSpeedError method | 3
2.04 | Create unit test for calculateSpeedError | 3
2.05 | Inspect source code | 3
2.06 | Implement solve method | 4
2.07 | Create unit test for solve | 4
2.08 | Inspect source code | 4
2.09 | Implement calculteWheelSpeed method | 4
2.1 | Create unit test for calculateWheelSpeed | 4
2.11 | Implement calculateWheelAngles method | 4
2.12 | Create unit test for calculateWheelAngles | 4
2.13 | Inspect source code | 4
2.14 | Implement Main function | 4
2.15 | Create visualization | 5
2.16 | Tune parameters | 5
2.17 | Update readme | 5
Remaining effort
Total effort time

## Iteration backlog - 1
MT08 - Markose Jacob, Pooja Kabra
Acme Ackermann Steering Controller
Iteration Backlog 1
Unique ID | Task | Target time (minutes) | Actual Time | Status
1 | Plan and Design | 0 | 0
1.01 | Link github repo with travis CI
1.02 | Link github repo with Coveralls
1.03 | Create skeleton code for Sensor class
1.04 | Write constructors and destructors for Sensor class
1.05 | Create unit tests for Sensor class
1.06 | Write getters for Sensor class
1.07 | Write setters for Sensor class
1.08 | Create skeleton code for RobotKinematics class
1.09 | Write constructors and destructors for RobotKinematics class
1.1 | Create unit tests for RobotKinematics Class
1.11 | Write getters for RobotKinematics class
1.12 | Write setters for RobotKinematics class
1.13 | Inspect source code
1.14 | Create skeleton code for Controller class
1.15 | Write constructors and destructors for Controller class
1.16 | Create unit tests for Controller class
1.17 | Write getters for Controller class
1.18 | Write setters for Controller class
1.19 | Create skeleton code for ForwardKinematics class
1.2 | Write constructors and destructors for ForwardKinematics class
1.21 | Create skeleton code for InverseKinematics class
1.22 | Inspect source code
1.23 | Inspect unit test
1.24 | Update readme

## Iteration backlog - 2
MT08 - Markose Jacob, Pooja Kabra
Acme Ackermann Steering Controller
Iteration Backlog 2
Unique ID | Task | Target time (minutes) | Actual Time | Status
2 | Implementation | 0 | 0
2.01 | Implement calculateHeadingError method
2.02 | Create unit test for calculateHeadingError
2.03 | Implement calculateSpeedError method
2.04 | Create unit test for calculateSpeedError
2.05 | Inspect source code
2.06 | Implement solve method
2.07 | Create unit test for solve
2.08 | Inspect source code
2.09 | Implement calculteWheelSpeed method
2.1 | Create unit test for calculateWheelSpeed
2.11 | Implement calculateWheelAngles method
2.12 | Create unit test for calculateWheelAngles
2.13 | Inspect source code
2.14 | Implement Main function
2.15 | Create visualization
2.16 | Tune parameters
2.17 | Update readme

## Work log
MT08 - Markose Jacob, Pooja Kabra
Acme Ackermann Steering Controller
Work/ Time log
Process Enactment |  | Pair Programming Roles | [5 empty] | Interrupt
Task | Comment | Driver | Navigator | Design Keeper | Date | Start | End | # | Time | Clean time
Iteration 1
1.01 | Link github repo with travis CI | Markose | Pooja | Pooja
1.02 | Link github repo with Coveralls | Markose | Pooja | Pooja
1.03 | Create skeleton code for Sensor class | Markose | Pooja | Pooja
1.04 | Write constructors and destructors for Sensor class | Markose | Pooja | Pooja
1.05 | Create unit tests for Sensor class | Markose | Pooja | Pooja
1.06 | Write getters for Sensor class | Markose | Pooja | Pooja
1.07 | Write setters for Sensor class | Markose | Pooja | Pooja
1.08 | Create skeleton code for RobotKinematics class | Markose | Pooja | Pooja
1.09 | Write constructors and destructors for RobotKinematics class | Markose | Pooja | Pooja
1.1 | Create unit tests for RobotKinematics Class | Markose | Pooja | Pooja
1.11 | Write getters for RobotKinematics class | Markose | Pooja | Pooja
1.12 | Write setters for RobotKinematics class | Markose | Pooja | Pooja
1.13 | Inspect source code | Pooja | Markose | -
1.14 | Create skeleton code for Controller class | Markose | Pooja | Pooja
1.15 | Write constructors and destructors for Controller class | Markose | Pooja | Pooja
1.16 | Create unit tests for Controller class | Markose | Pooja | Pooja
1.17 | Write getters for Controller class | Markose | Pooja | Pooja
1.18 | Write setters for Controller class | Markose | Pooja | Pooja
1.19 | Create skeleton code for ForwardKinematics class | Markose | Pooja | Pooja
1.2 | Write constructors and destructors for ForwardKinematics class | Markose | Pooja | Pooja
1.21 | Create skeleton code for InverseKinematics class | Markose | Pooja | Pooja
1.22 | Inspect source code | Pooja | Markose | -
1.23 | Inspect unit test | Pooja | Markose | -
1.24 | Update readme | Pooja | Markose | -
Iteration 2
2.01 | Implement calculateHeadingError method | Pooja | Markose | Markose
2.02 | Create unit test for calculateHeadingError | Pooja | Markose | Markose
2.03 | Implement calculateSpeedError method | Pooja | Markose | Markose
2.04 | Create unit test for calculateSpeedError | Pooja | Markose | Markose
2.05 | Inspect source code | Pooja | Markose | Markose
2.06 | Implement solve method | Pooja | Markose | Markose
2.07 | Create unit test for solve | Pooja | Markose | Markose
2.08 | Inspect source code | Pooja | Markose | Markose
2.09 | Implement calculteWheelSpeed method | Pooja | Markose | Markose
2.1 | Create unit test for calculateWheelSpeed | Pooja | Markose | Markose
2.11 | Implement calculateWheelAngles method | Pooja | Markose | Markose
2.12 | Create unit test for calculateWheelAngles | Pooja | Markose | Markose
2.13 | Inspect source code | Pooja | Markose | Markose
2.14 | Implement Main function | Pooja | Markose | Markose
2.15 | Create visualization | Pooja | Markose | Markose
2.16 | Tune parameters | Pooja | Markose | Markose
2.17 | Update readme | Pooja | Markose | Markose